## Instructions
Construction Material Test Documentation Framework
Digital artefact for slump test and compressive strength test documentation - case study: Nigeria
This workbook is the artefact for the dissertation "A Framework for Digitalising the Documentation of Construction Material Test Results in Nigeria: The Case of Slump and Compressive Strength Testing". It replaces paper logbooks and standalone Excel sheets with a single, structured, traceable spreadsheet system covering sample registration, slump testing, curing, compressive strength testing, and reporting. The sheets below are populated with data drawn from realistic Nigerian construction projects, so the workflow can be demonstrated end-to-end.
Section | Purpose
How to use this workbook
1. Sample Registration | Every concrete batch is registered here first. Each sample has a unique ID that all other sheets refer to.
2. Slump Test | Fresh-concrete slump results at the point of testing, linked to a ID.
3. Curing & Compressive Strength | The 7 / 14 / 21 / 28-day curing cycle, with load and cross-sectional area entered and compressive strength calculated automatically.
4. Reporting & Traceability | A live summary and non-conformance log drawn automatically from the three data sheets.
5. Dropdown lists | The Lists sheet holds the fixed values used in dropdown menus (roles, concrete grades, curing ages, status). Edit it only if these categories change.
Colour / formatting key
Grey header row | Column headers - do not edit.
White (unshaded) cell | Data entry field.
Bold black text | Calculated field - do not overwrite; formula updates automatically.
Light grey shaded rows | Populated data - edit or replace with data if needed.
Legend
Header row / section divider (grey fill)
Populated data row (very light grey fill)
Bold text | Automatically calculated - do not type over

## Lists
Role | Concrete Grade | Test Status | Curing Age (days)
Lab Technician | Grade 10 | Scheduled | 7
Site Engineer | Grade 20 | In Progress | 14
Project Manager | Grade 25 | Completed | 21
| Grade 30 | Non-Conforming | 28
Grade 35
Grade 40
Reference lists used for dropdown menus on the data-entry sheets. Edit values here to update every dropdown at once.

## Registration
Registration
Every concrete batch is registered here and given a unique ID used across all other sheets.
Sample ID | Project Name | Batch No. | Mixer ID | Casting Date | Concrete Grade | Registered By | Role | Notes
SMP-0001 | Lagos-Ibadan Expressway Rehabilitation | B-001 | MX-01 | 2026-08-01 | Grade 20 | User 1 | Lab Technician | Routine batch check
SMP-0002 | Abuja Light Rail Extension | B-002 | MX-02 | 2026-08-02 | Grade 25 | User 2 | Lab Technician | First pour of the week
SMP-0003 | Port Harcourt Housing Estate | B-003 | MX-03 | 2026-08-03 | Grade 30 | User 3 | Site Engineer | Client witness present
SMP-0004 | Kano Ring Road Upgrade | B-004 | MX-04 | 2026-08-04 | Grade 25 | User 4 | Lab Technician | Rain delay - poured mid-morning
SMP-0005 | Enugu Flyover Bridge | B-005 | MX-01 | 2026-08-05 | Grade 20 | User 5 | Project Manager | Re-test scheduled after mix adjustment
SMP-0006 | Kaduna Industrial Layout | B-006 | MX-02 | 2026-08-06 | Grade 35 | User 6 | Site Engineer | Standard delivery
SMP-0007 | Ibadan-Ogbomoso Highway | B-007 | MX-03 | 2026-08-07 | Grade 25 | User 7 | Lab Technician | New mixer commissioned
SMP-0008 | Onitsha Market Complex | B-008 | MX-04 | 2026-08-08 | Grade 30 | User 8 | Site Engineer | Weekend pour
SMP-0009 | Benin City Drainage Project | B-009 | MX-01 | 2026-08-09 | Grade 20 | User 9 | Lab Technician | Site engineer inspection
SMP-0010 | Warri Refinery Access Road | B-010 | MX-02 | 2026-08-10 | Grade 25 | User 10 | Project Manager | Quarterly compliance sample
SMP-0011 | Abeokuta Water Treatment Plant | B-011 | MX-03 | 2026-08-11 | Grade 30 | User 1 | Lab Technician | Routine batch check
SMP-0012 | Jos Plateau Housing Scheme | B-012 | MX-04 | 2026-08-12 | Grade 25 | User 2 | Lab Technician | First pour of the week
SMP-0013 | Uyo Stadium Access Road | B-013 | MX-01 | 2026-08-13 | Grade 20 | User 3 | Site Engineer | Client witness present
SMP-0014 | Owerri Government Secretariat | B-014 | MX-02 | 2026-08-14 | Grade 35 | User 4 | Lab Technician | Rain delay - poured mid-morning
SMP-0015 | Calabar Free Trade Zone Extension | B-015 | MX-03 | 2026-08-15 | Grade 25 | User 5 | Project Manager | Re-test scheduled after mix adjustment
SMP-0016 | Ilorin-Jebba Highway | B-016 | MX-04 | 2026-08-16 | Grade 30 | User 6 | Site Engineer | Standard delivery
SMP-0017 | Sokoto Central Market Rebuild | B-017 | MX-01 | 2026-08-17 | Grade 20 | User 7 | Lab Technician | New mixer commissioned
SMP-0018 | Minna Airport Road | B-018 | MX-02 | 2026-08-18 | Grade 25 | User 8 | Site Engineer | Weekend pour
SMP-0019 | Yenagoa Bridge Project | B-019 | MX-03 | 2026-08-19 | Grade 30 | User 9 | Lab Technician | Site engineer inspection
SMP-0020 | Zaria Teaching Hospital Annex | B-020 | MX-04 | 2026-08-20 | Grade 25 | User 10 | Project Manager | Quarterly compliance sample

## Slump Test
Slump Test
Fresh-concrete workability results, linked to a registered ID.
Sample ID | Test Date | Concrete Grade | Slump (mm) | Acceptance Limit (mm) | Within Limit? | Tested By | Witnessed By | Notes
SMP-0001 | 2026-08-01 | Grade 20 | 72 | 90 | Yes | User 1 | Witness 1 | Within acceptable range
SMP-0002 | 2026-08-02 | Grade 25 | 80 | 90 | Yes | User 2 | Witness 2 | Within acceptable range
SMP-0003 | 2026-08-03 | Grade 30 | 68 | 100 | Yes | User 3 | Witness 3 | Within acceptable range
SMP-0004 | 2026-08-04 | Grade 25 | 95 | 90 | No - Non-Conforming | User 4 | Witness 4 | Mix adjusted for re-pour
SMP-0005 | 2026-08-05 | Grade 20 | 60 | 90 | Yes | User 5 | Witness 5 | Within acceptable range
SMP-0006 | 2026-08-06 | Grade 35 | 85 | 100 | Yes | User 6 | Witness 6 | Within acceptable range
SMP-0007 | 2026-08-07 | Grade 25 | 78 | 90 | Yes | User 7 | Witness 7 | Within acceptable range
SMP-0008 | 2026-08-08 | Grade 30 | 92 | 100 | Yes | User 8 | Witness 8 | Within acceptable range
SMP-0009 | 2026-08-09 | Grade 20 | 65 | 90 | Yes | User 9 | Witness 9 | Within acceptable range
SMP-0010 | 2026-08-10 | Grade 25 | 70 | 90 | Yes | User 10 | Witness 10 | Within acceptable range
SMP-0011 | 2026-08-11 | Grade 30 | 88 | 100 | Yes | User 1 | Witness 1 | Within acceptable range
SMP-0012 | 2026-08-12 | Grade 25 | 82 | 90 | Yes | User 2 | Witness 2 | Within acceptable range
SMP-0013 | 2026-08-13 | Grade 20 | 96 | 90 | No - Non-Conforming | User 3 | Witness 3 | Mix adjusted for re-pour
SMP-0014 | 2026-08-14 | Grade 35 | 75 | 100 | Yes | User 4 | Witness 4 | Within acceptable range
SMP-0015 | 2026-08-15 | Grade 25 | 63 | 90 | Yes | User 5 | Witness 5 | Within acceptable range
SMP-0016 | 2026-08-16 | Grade 30 | 90 | 100 | Yes | User 6 | Witness 6 | Within acceptable range
SMP-0017 | 2026-08-17 | Grade 20 | 79 | 90 | Yes | User 7 | Witness 7 | Within acceptable range
SMP-0018 | 2026-08-18 | Grade 25 | 55 | 90 | Yes | User 8 | Witness 8 | Within acceptable range
SMP-0019 | 2026-08-19 | Grade 30 | 84 | 100 | Yes | User 9 | Witness 9 | Within acceptable range
SMP-0020 | 2026-08-20 | Grade 25 | 91 | 90 | No - Non-Conforming | User 10 | Witness 10 | Mix adjusted for re-pour

## Curing and Strength
Curing and Compressive Strength
7 / 14 / 21 / 28-day curing schedule with automatic compressive-strength calculation.
Sample ID | Casting Date | Curing Age (days) | Test Date | Cube Ref. | Load (kN) | Cross-Sec. Area (mm2) | Compressive Strength (N/mm2) | Acceptance Limit (N/mm2) | Result | Tested By
SMP-0001 | 2026-08-01 | 7 | 2026-08-08 | CB-001-1 | 279 | 22500 | 12.4 | 20 | In Progress | User 1
SMP-0001 | 2026-08-01 | 14 | 2026-08-15 | CB-001-2 | 369 | 22500 | 16.4 | 20 | In Progress | User 1
SMP-0001 | 2026-08-01 | 21 | 2026-08-22 | CB-001-3 | 418.5 | 22500 | 18.6 | 20 | In Progress | User 1
SMP-0001 | 2026-08-01 | 28 | 2026-08-29 | CB-001-4 | 459 | 22500 | 20.4 | 20 | Pass | User 1
SMP-0002 | 2026-08-02 | 7 | 2026-08-09 | CB-002-1 | 348.8 | 22500 | 15.5 | 25 | In Progress | User 2
SMP-0002 | 2026-08-02 | 14 | 2026-08-16 | CB-002-2 | 461.2 | 22500 | 20.5 | 25 | In Progress | User 2
SMP-0002 | 2026-08-02 | 21 | 2026-08-23 | CB-002-3 | 523.1 | 22500 | 23.25 | 25 | In Progress | User 2
SMP-0002 | 2026-08-02 | 28 | 2026-08-30 | CB-002-4 | 573.8 | 22500 | 25.5 | 25 | Pass | User 2
SMP-0003 | 2026-08-03 | 7 | 2026-08-10 | CB-003-1 | 418.5 | 22500 | 18.6 | 30 | In Progress | User 3
SMP-0003 | 2026-08-03 | 14 | 2026-08-17 | CB-003-2 | 553.5 | 22500 | 24.6 | 30 | In Progress | User 3
SMP-0003 | 2026-08-03 | 21 | 2026-08-24 | CB-003-3 | 627.8 | 22500 | 27.9 | 30 | In Progress | User 3
SMP-0003 | 2026-08-03 | 28 | 2026-08-31 | CB-003-4 | 688.5 | 22500 | 30.6 | 30 | Pass | User 3
SMP-0004 | 2026-08-04 | 7 | 2026-08-11 | CB-004-1 | 348.8 | 22500 | 15.5 | 25 | In Progress | User 4
SMP-0004 | 2026-08-04 | 14 | 2026-08-18 | CB-004-2 | 461.2 | 22500 | 20.5 | 25 | In Progress | User 4
SMP-0004 | 2026-08-04 | 21 | 2026-08-25 | CB-004-3 | 523.1 | 22500 | 23.25 | 25 | In Progress | User 4
SMP-0004 | 2026-08-04 | 28 | 2026-09-01 | CB-004-4 | 573.8 | 22500 | 25.5 | 25 | Pass | User 4
SMP-0005 | 2026-08-05 | 7 | 2026-08-12 | CB-005-1 | 279 | 22500 | 12.4 | 20 | In Progress | User 5
SMP-0005 | 2026-08-05 | 14 | 2026-08-19 | CB-005-2 | 369 | 22500 | 16.4 | 20 | In Progress | User 5
SMP-0005 | 2026-08-05 | 21 | 2026-08-26 | CB-005-3 | 418.5 | 22500 | 18.6 | 20 | In Progress | User 5
SMP-0005 | 2026-08-05 | 28 | 2026-09-02 | CB-005-4 | 459 | 22500 | 20.4 | 20 | Pass | User 5
SMP-0006 | 2026-08-06 | 7 | 2026-08-13 | CB-006-1 | 488.2 | 22500 | 21.7 | 35 | In Progress | User 6
SMP-0006 | 2026-08-06 | 14 | 2026-08-20 | CB-006-2 | 645.8 | 22500 | 28.7 | 35 | In Progress | User 6
SMP-0006 | 2026-08-06 | 21 | 2026-08-27 | CB-006-3 | 732.4 | 22500 | 32.55 | 35 | In Progress | User 6
SMP-0006 | 2026-08-06 | 28 | 2026-09-03 | CB-006-4 | 803.3 | 22500 | 35.7 | 35 | Pass | User 6
SMP-0007 | 2026-08-07 | 28 | 2026-09-04 | CB-007-1 | 573.8 | 22500 | 25.5 | 25 | Pass | User 7
SMP-0008 | 2026-08-08 | 28 | 2026-09-05 | CB-008-1 | 607.5 | 22500 | 27 | 30 | Fail - Non-Conforming | User 8
SMP-0009 | 2026-08-09 | 28 | 2026-09-06 | CB-009-1 | 459 | 22500 | 20.4 | 20 | Pass | User 9
SMP-0010 | 2026-08-10 | 28 | 2026-09-07 | CB-010-1 | 573.8 | 22500 | 25.5 | 25 | Pass | User 10
SMP-0011 | 2026-08-11 | 28 | 2026-09-08 | CB-011-1 | 688.5 | 22500 | 30.6 | 30 | Pass | User 1
SMP-0012 | 2026-08-12 | 28 | 2026-09-09 | CB-012-1 | 573.8 | 22500 | 25.5 | 25 | Pass | User 2
SMP-0013 | 2026-08-13 | 28 | 2026-09-10 | CB-013-1 | 459 | 22500 | 20.4 | 20 | Pass | User 3
SMP-0014 | 2026-08-14 | 28 | 2026-09-11 | CB-014-1 | 803.3 | 22500 | 35.7 | 35 | Pass | User 4
SMP-0015 | 2026-08-15 | 28 | 2026-09-12 | CB-015-1 | 506.2 | 22500 | 22.5 | 25 | Fail - Non-Conforming | User 5
SMP-0016 | 2026-08-16 | 28 | 2026-09-13 | CB-016-1 | 688.5 | 22500 | 30.6 | 30 | Pass | User 6
SMP-0017 | 2026-08-17 | 28 | 2026-09-14 | CB-017-1 | 459 | 22500 | 20.4 | 20 | Pass | User 7
SMP-0018 | 2026-08-18 | 28 | 2026-09-15 | CB-018-1 | 506.2 | 22500 | 22.5 | 25 | Fail - Non-Conforming | User 8
SMP-0019 | 2026-08-19 | 28 | 2026-09-16 | CB-019-1 | 688.5 | 22500 | 30.6 | 30 | Pass | User 9
SMP-0020 | 2026-08-20 | 28 | 2026-09-17 | CB-020-1 | 573.8 | 22500 | 25.5 | 25 | Pass | User 10

## Reporting
Reporting and Traceability
Summary Metric | Value
Total samples registered | 20
Total slump tests recorded | 20
Slump tests non-conforming | 3
Total compressive strength tests recorded | 38
Compressive strength tests failed | 3
Compressive strength tests passed | 17
Non-Conformance Log (auto-flagged)
Sheet | Sample ID | Issue | Date Flagged
Slump Test | SMP-0004 | Slump 95mm exceeds 90mm limit | 2026-08-04
Slump Test | SMP-0013 | Slump 96mm exceeds 90mm limit | 2026-08-13
Slump Test | SMP-0020 | Slump 91mm exceeds 90mm limit | 2026-08-20
Curing and Strength | SMP-0008 | 28-day compressive strength below acceptance limit | 2026-09-05
Curing and Strength | SMP-0015 | 28-day compressive strength below acceptance limit | 2026-09-12
Curing and Strength | SMP-0018 | 28-day compressive strength below acceptance limit | 2026-09-15

## Chart Data (hidden)
Curing Age (days) | SMP-0001 | SMP-0002 | SMP-0003 | SMP-0004 | SMP-0005 | SMP-0006
7 | 12.4 | 15.5 | 18.6 | 15.5 | 12.4 | 21.7
14 | 16.4 | 20.5 | 24.6 | 20.5 | 16.4 | 28.7
21 | 18.6 | 23.25 | 27.9 | 23.25 | 18.6 | 32.55
28 | 20.4 | 25.5 | 30.6 | 25.5 | 20.4 | 35.7
Outcome | Count
Pass | 17
Fail - Non-Conforming | 3
In Progress | 18
Test Type | Non-Conforming Count
Slump Test | 3
Compressive Strength Test | 3